## DEQ Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Develop an inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time | Track number of existing stations and report new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks/public areas with stations. Add a percentage of stations added until 100% of parks/public areas that need stations have stations. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volume (Post Construction). | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track the features installed, size and treatment expectations as they are installed. | Ongoing as development occurs. | This strategy is tied into the Phase II program and dependent on funding availability to design and construct capital improvements, as well as on private investment in new or redevelopment projects. Report out on features being installed and maintained in capital projects that incorporate these. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education through design workshops, volunteer opportunities, and/or other methods. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Part of phase II program. Annual update on program development and relevant statistics in Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Address water quality impacts of stormwater | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Pollution Prevention/Good Housekeeping - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage, sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). | Review and refine illicit discharge and hot spot water sampling program as needed | Staff Time. RVCOG | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Annual update on actions taken in NPDES Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time. RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. | Staff time. RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Note on C49: Greg Stabach: This looks like the "adaptive management" portion of the plan
Note on G19: Greg Stabach: List/map of locations. Could be an online map (e.g., RVS) or developed using other tool (ArcGis, Survey 1-2-3)

## Temp
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Implement current riparian buffer standards/riparian ordinance | Review site and land division proposals to ensure consistent buffers. Implement and enforce riparian ordinance | Staff Time | List of riparian buffer standards or riparian ordinance actions taken. | Ongoing | Annual reports will track buffer standards or riparian ordinance actions taken. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Incentivize new land division proposals to reserve floodplains as a natural open space | Review site and land division proposals for opportunities | Staff time | Program development. Keep records of protected areas. | Ongoing | Annual reports and 5-year reviews will track progress including number of projects, acres preserved/restored, and establish recommendations for improvements as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for implementation of projects (active management of invasives, planting, etc.). RVCOG. Contractor(s), partners. | Line item established in budget with annual funding. | first year with line item and funding; annually thereafter | Budget development and reporting will demonstrate progress. Number of plantings or projects. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. | Staff time, RVCOG, partners. | Completion and record of annual efforts | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City participates in events: Events include at least one featured tree planting project, tree giveaways to residents, or restoration project activity (monitoring, maintenance, watering, invasive species management). | Staff time, RVCOG, partners. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | Events held each year with local participants and activities that educate and implement tree planting. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time, RVCOG, partners. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify Implemented projects on an annual basis | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Reduce warm stormwater runoff volumes (Post Construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from stormwater utility fund, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects (mostly vegetative buffer strips and such associated with new road projects) that incorporated LID or other methods into development and redevelopment plans. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Note on D14: Greg Stabach: The intent of this line item is to fund a planting program to implement projects. The thought is to mirror the Bear Creek Monitoring Program and develop a planting program to fund and complete projects annually.

## Ed and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter and/or other publications. | Staff. RVCOG. Partners. | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics | Staff time, RVCOG | City’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Example: Rain Garden, downspout disconnects, demonstration workshops, Salmon Watch Program, don’t feed wildlife etc | Continue to support the Regional Programs by working with RVCOG. Additional Grants Pass specific programs will be conducted by City Staff, RVCOG, and/or volunteers. | Workshop/Program participation and measurable results (i.e. number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.) | Annually | Annual Action Plan and Subsequent Report | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns | Staff time & support funding. | City’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. | Staff time. RVCOG. Other DMAs. Partners. Volunteers | Focus is on identifying, prioritizing, and moving toward implementation of projects | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. | Staff time. RVCOG. Partners. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025